## Tab A - Project Application
Missouri State Emergency Management Agency
2302 Militia Drive (65101)
PO Box 116 (65102)
Jefferson City, Missouri
Hazard Mitigation Grant Program (HMGP)
Safe Room Project Application
Update 7-1-2025
What is the Hazard Mitigation Grant Program?
Authorized under Section 404 of the Stafford Act, the Hazard Mitigation Grant Program (HMGP) is funded by the Federal Emergency Management Agency (FEMA) to provide grants to State and local governments to implement long-term mitigation measures after a major disaster declaration. The purpose of the program is to reduce loss of life and property damage resulting from natural disasters by funding eligible mitigation measures to be implemented during the recovery from a disaster.
1) Project must conform to Missouri's Hazard Mitigation Plan. To review the State of Missouri's Hazard Mitigation Plan, follow the link: https://sema.dps.mo.gov/docs/programs/LRMF/mitigation/MO_Hazard_Mitigation_Plan2018.pdf
2) Applicant must have a FEMA-approved Local Hazard Mitigation Plan, and the project must conform to the local plan.
3) Project must provide a beneficial impact on the disaster area (i.e. the State of Missouri).
4) Project must undergo environmental and historic preservation review process to ensure compliance.
5) Project must solve a problem independently or constitute a functional portion of a solution, which as a whole will be completed.
6) City/County must be NFIP compliant and a participant in good standing, if required.
7) Project must be cost-effective and substantially reduce the risk of future damage, hardship, loss of life, or suffering resulting from a major disaster.
Benefit-Cost Analysis:
Projects funded by the HMGP must be cost-effective. To determine cost-effectiveness applicants must use FEMA's Benefit Cost Analysis Resource Kit Version available for download at www.bcahelpline.com. If you have problems with the download, contact FEMA's Technical Assistance Helpline. The Helpline can be reached from 9 am - 5 pm (ET), Monday through Friday, toll-free at 1-855-540-6744 or by e-mail at bchelpline@fema.dhs.gov. This application will require a BCA to be performed.
Completing the HMGP Application:
This application will enable you to apply for post disaster Hazard Mitigation Grant Program funding. This application is designed to capture the necessary information to meet program requirements. Applicants are encouraged to take ample time, read through the questions carefully, and complete each of the sections. This will enable you to move through the application process most efficiently.
Project Applications must be completed in this MS Excel format by email or on a flash drive and mailed to: (See Below) Save as "Applicant Name, HMGP, Type of Project." The Benefit Cost Analysis module(s) must be provided electronically. State Mitigation staff will work with you to ensure your application is correct and complete, which may require multiple revisions.
Missouri State Emergency Management Agency
Attn: Heidi Carver - Mitigation Section
2302 Militia Drive
PO Box 116
Jefferson City, Missouri 65101
I. Applicant Information | [5 empty] | DATE:
| A. Applicant/Community Name |  |  | B. Address |  |  | City, State, Zip Code
| C. Point of Contact (POC) Name for Project |  |  | POC Title | POC Agency |  | POC Email
| POC PO Box and Zip Code |  | POC Street Address |  | POC City, State, Zip Code |  |  | POC Phone
| Alternate POC Name or Authorized Representative |  |  | Alt POC Title | Alt POC Agency |  | Alternate POC Email
| Alt POC PO Box and Zip Code |  | Alt POC Street Address |  | Alt POC City, State, Zip Code |  |  | Alt POC Phone
| D. Federal Tax ID # / EIN |  |  | E. UEI Number |  |  | F. FIPS Code
| G. County Name |  |  | H. US Congressional District(s) |  | State Legislative Districts
[6 empty] | Senate |  | House
| I. Is the Applicant/Community participating in the National Flood Insurance Program (NFIP)? |  |  |  |  | Community's CID Number
J. Descriptive Project Title
K. Description of Project Location, (i.e., Latitude and Longitude readings taken from the approximate center of the proposed project site, Neighborhood, Subdivision, Geographic Boundaries, Driving Directions, etc.)
II. Project Information
A. Describe the problem to be mitigated.
B. Summary Scope of Work
Provide a detailed description of the proposed project and work to be accomplished.
C. Local Mitigation Plan Information
1. Title of Applicant/Community's Local Hazard Mitigation Plan & Date Approved:
2a. Mitigation strategy, measure(s), action or objective that this proposed project will address:
2b. Location in the Local Plan (section, page #) where the mitigation measure(s), action or objective is identified:
3. How does the proposed project conform to the State of Missouri and local mitigation goals? Explain:
D. Will the proposed mitigation measure provide an independent and long-term solution to the problem? Consider anticipated long-term changes to the community. Explain:
E. How does the proposed mitigation measure address a repetitive problem or a problem that poses a significant risk to public health and life safety if left unresolved? Is an accessible and effective warning systems in place to notify prospective community safe room occupants, including those with disabilities, when they should evacuate to the safe room facility. Explain:
F. How will the proposed mitigation measure substantially reduce future disaster losses, including the risk of future damage, hardship, loss, and/or suffering? Explain:
G. Will the community suffer detrimental impacts (loss of life, loss of essential services, damage to critical facilities, economic hardship) if the proposed mitigation measure is not implemented? Explain:
H. Describe damages caused by previous and current disaster and their associated costs - use historical data.
I. Hazard(s) to be Mitigated / Level of Protection
1. Select the type(s) of hazard(s) the proposed project will mitigate.
|  | Tornado |  | Yes |  | Windstorm |  | Yes
|  |  |  | Yes |  |  |  | Yes
|  |  |  | No |  |  |  | No
2. Number of people (target population) protected by the proposed project:
# of People
3. Provide the level of protection that the proposed project will provide. (Note: In Missouri, all tornado saferooms must protect to 250 mph winds.)
mph wind.
| 4. The proposed project will provide protection against the specified hazard(s) for | [7 empty] | years.
Please explain the methodology used to determine the useful life of the project (i.e., FEMA default value, etc.)
III. Discussion of Project Alternatives - Proposed Project and 2 Alternatives
A. Project descriptions and impacts (both beneficial and detrimental)
1. Do Nothing Alternative:
2. Proposed Project:
3. Other Feasible Alternative (include estimated costs, if available):
B. Justification for choosing the proposed project - discuss how the proposed project is the most practical, effective and environmentally sound alternative of the alternatives.
C. Describe how the proposed project best fits within the overall emergency response plan for the community.
IV. Project Compliance Assurances
A. Code Compliance
Will the project meet all applicable written codes and standards for the local jurisdiction?
|  | Building |  | Select One | Zoning |  | Select One
Local Code
IBC 2006, if no local code
|  | Public Notification |  | Local Code | Other
Identify necessary permits, variances or exemptions:
Building:
Zoning:
Public Notifications:
B. Floodplain Ordinance
If the project is located in a special flood hazard area (also known as a 100-year floodplain) or the 500-year floodplain, the local floodplain ordinance may require a floodplain permit for this project. Tornado saferooms CANNOT be built in floodplains. Contact SEMA before moving forward.
|  |  |  | Floodplain Permit Required |  | Select One
Yes
No
V. Project Cost Information
A. Estimated Project Cost & Shares - Do not change the budget from the NOI unless you have received approval from the SEMA Grant Manager or State Hazard Mitigation Officer.
Include any budget source documents (bid quotes/sheets, estimates, etc.) with the paper application.
| Funding Sources |  |  | Funding Amount |  | % of Total Cost
| Federal |  |  |  |  | 75%
| State |  |  |  |  | 10%
| Local |  |  |  |  | 15%
| Total Proposed Project Cost |  |  |  |  | 100%
B. Non-Federal/Local Cost Share Sources
Identify the estimated make-up of the local cost share. Attach supporting documentation as necessary.
|  | Local Cash |  |  | Select One
Yes
No
|  | Local In-Kind Services |  |  | Select One
|  | Local In-Kind Goods |  |  | Select One
|  | Other (explain) |  |  | Select One
Explanation of Other:
C. Cost Effectiveness Information
Attach the Benefit-Cost Analysis (BCA) for this project and all supporting documentation used to determine the BCA.
Net Present Value of Project Benefits
Total Project Cost Estimate
Benefit-Cost Ratio for the Project
VI. Work Schedule
A. List the major milestones for this project.
| Task |  |  | TimeFrame in Months
Total Project Duration:
B. Provide maintenance and cleaning schedule for the useful life of the project (identify who is responsible) and estimated annual maintenance costs. If the entity/responsibly party for regular long-term maintenance is different than the entity signing and certifying this application, please attach a letter from the entity accepting performance responsibility.
VII. Certifications | Certifications
To the best of my knowledge and belief, I certify that all data in this application packet is complete, true and correct. The governing body of the applicant has duly authorized this document and hereby applies for assistance as documented in this application. The applicant understands that the project shall not proceed until FEMA approval is granted.
| Signature of Chief Executive Officer |  |  |  | Signature of the Authorized Representative
| Name of the Chief Executive Officer |  |  |  | Name of Authorized Representative
| Title |  |  |  | Title
| Organization |  |  |  | Organization
| Date |  |  |  | Date
| Phone Number |  |  |  | PO Box / Street Address
City, State and Zip Code
Phone Number
Email Address

## Tab B - Detailed SOW
Scope of Work - Detailed Narrative
Applicant:
Project Title:
Provide a detailed narrative of the proposed project and work to be accomplished. Be sure to specify in what phase of the project the activity will be completed, if applicable.

## Tab C1 - Detailed Cost Estimate
* Line items and values are examples only
Item | Description | Final Quantity | Final Units | Final Unit Price | Final Total | FEMA Elligible | Non-FEMA Elligible
1 | Site
| Excavation (Building SF +10%) | 9656 | SF | 2.59 | 25009.04 | 25009.04
| Building Pad Preparation (Building SF +10%) | 9656 | SF | 5.91 | 57066.96 | 57066.96
| Site Grading (Building SF +10%) | 9656 | SF | 5.7 | 55039.2 | 55039.2
| Erosion Control & SWPP (50ft Beyond Perimeter) | 791 | LF | 4.74 | 3749.34 | 3749.34
| Storm Piping (Perimeter of Building +40%) | 547 | LF | 6.1 | 3336.7 | 3336.7
| Low Volume Change (50% of Perimeter) | 195 | LF | 85.48 | 16668.6 | 16668.6
| Entry Pads (7.5% of SF) | 658 | SF | 8.87 | 5836.46 | 5836.46
| SUBTOTAL (Site) |  |  |  | 166706.3 | 166706.3 | 0
2 | Structural
| Continuous Perimeter Footing | 391 | LF | 42.63 | 16668.33 | 16668.33
| Interior Footings (5% of Building SF) | 439 | SF | 53.15 | 23332.85 | 23332.85
| Gravel Backfill (Building SF +10%) | 9656 | SF | 5.52 | 53301.12 | 53301.12
| Slab on Grade (Building SF) | 8778 | SF | 13.86 | 121663.08 | 121663.08
| Pre-Cast Walls (Main Stuctural System) | 391 | LF | 549.92 | 215018.72 | 215018.72
| Stuctural Steel | 8778 | SF | 11.39 | 99981.42 | 99981.42
| Embeds/Edge Angles | 391 | LF | 29.84 | 11667.44 | 11667.44
| Bar Joists | 4389 | LF | 12.15 | 53326.35 | 53326.35
| Roof Decking | 8788 | SF | 3.42 | 30054.96 | 30054.96
| Slab on Roof Deck | 8788 | SF | 3.8 | 33394.4 | 33394.4
| Roof Ladder | 1 | EA | 5000 | 5000 | 5000
| Railings | 129 | LF | 25.84 | 3333.36 | 3333.36
| SUBTOTAL (Structural) |  |  |  | 666742.03 | 666742.03 | 0
3 | Architectural
| Foundation Perimeter Insulation | 391 | LF | 11.07 | 4328.37 | 4328.37
| Foundation Moisture/Air Barrier | 391 | LF | 4.92 | 1923.72 | 1923.72
| Slab on Grade Moisture/Air Barrier | 8778 | SF | 0.66 | 5793.48 | 5793.48
| Exterior Caulking | 544 | SF | 1.77 | 962.88 | 962.88
| Roof Deck Insulation | 8448 | SF | 4.16 | 35143.68 | 35143.68
| Roofing | 8448 | SF | 5.7 | 48153.6 | 48153.6
| Parapet Coping | 391 | LF | 11.07 | 4328.37 | 4328.37
| Scuppers, Downspouts, and Gutters | 391 | LF | 11.07 | 4328.37 | 4328.37
| Fascia and Soffit | 391 | LF | 7.38 | 2885.58 | 2885.58
| Flashing | 544 | LF | 2.65 | 1441.6 | 1441.6
| FEMA Hollow Metal Frame/Door | 9 | EA | 4594.44 | 41349.96 | 41349.96
| Hollow Metal Frames | 9 | EA | 604 | 5436 | 1442 | 3994
| Hollow Metal Doors | 5 | EA | 2480.8 | 12404 | 2404 | 10000
| Wood Doors | 4 | EA | 1740.5 | 6962 | 962 | 6000
| Wood Blocking | 544 | LF | 1.77 | 962.88 | 962.88
| Interior Partitions | 5706 | SF | 2.86 | 16319.16 | 11540 | 4779.16
| Sound Batt Insulation | 5706 | SF | 0.72 | 4108.32 | 2885 | 1223.32
| Gypsum Board Walls | 5706 | SF | 1.45 | 8273.7 | 5770 | 2503.7
| Gypsum Board Ceilings | 1317 | SF | 1.47 | 1935.99 | 1442 | 493.99
| Acoustical Ceilings | 2194 | SF | 0.89 | 1952.66 | 1442 | 510.66
| Interior Painting | 5706 | SF | 0.34 | 1940.04 | 0 | 1940.04
| Toilet Compartments & Accessories | 878 | SF | 20.37 | 17884.86 | 2885 | 14999.86
| Sealed Concrete Flooring | 8778 | SF | 0.49 | 4301.22 | 4301.22
| Graphics (Signs) | 18 | EA | 53.44 | 961.92 | 961.92
| SUBTOTAL (Architectural) |  |  |  | 234082.36 | 187637.63 | 46444.73
4 | Electrical
| Electrical Service | 8778 | SF | 1.66 | 14571.48 | 7052 | 7519.48
| Generator and Transfer Switch (100 kVA) | 8778 | SF | 5.84 | 51263.52 | 51263.52
| Transformer | 1 | EA | 17239 | 17239 | 8334 | 8905
| Wiring | 8778 | SF | 6.8 | 59690.4 | 28849 | 30841.4
| Panels | 5 | EA | 1326 | 6630 | 3205 | 3425
| Disconnect | 5 | EA | 1856 | 9280 | 4488 | 4792
| Outlets/Switches | 8778 | SF | 1.06 | 9304.68 | 4488 | 4816.68
| Lighting | 8778 | SF | 3.25 | 28528.5 | 13783 | 14745.5
| Fire Alarm | 8778 | SF | 0.33 | 2896.74 | 2885 | 11.74
| SUBTOTAL (Electrical) |  |  |  | 199404.32 | 124347.52 | 75056.8
5 | Mechanical
| HVAC Units/Equipment | 8778 | SF | 8.29 | 72769.62 | 36862 | 35907.62
| HVAC Controls | 8778 | SF | 1.15 | 10094.7 | 5128 | 4966.7
| HVAC Test/Balance (estimate) | 8778 | SF | 0.65 | 5705.7 | 2885 | 2820.7
| HVAC Supply and Return Ducting | 8778 | SF | 0.94 | 8251.32 | 4167 | 4084.32
| HVAC Diffusers/Grilles | 8778 | SF | 0.5 | 4389 | 2244 | 2145
| Plubming Supply Lines | 195 | LF | 104.49 | 20375.55 | 9296 | 11079.55
| Plumbing Waste Lines | 195 | LF | 86.96 | 16957.2 | 6731 | 10226.2
| Plumbing Vent Stacks | 195 | LF | 116.52 | 22721.4 | 9937 | 12784.4
| Plumbing Clean Outs | 98 | LF | 92.51 | 9065.98 | 3526 | 5539.98
| Plumbing Fixture - Sinks | 7 | EA | 1539.14 | 10773.98 | 4809 | 5964.98
| Plumbing Fixture - Toilets | 14 | EA | 1706.64 | 23892.96 | 10257 | 13635.96
| Plumbing Fixture - Drinking Fountain | 3 | EA | 3982.33 | 11946.99 | 5129 | 6817.99
| Plumbing Fixture - Mop Sink | 1 | EA | 1919 | 1919 | 0 | 1919
| Plumbing Water Heater(s) | 1 | EA | 13760 | 13760 | 0 | 13760
| Plumbing Fire Protection - Sprinker System | 8778 | SF | 1.72 | 15098.16 | 15098.16
| Plumbing Fire Protection - Fire/Smoke Detection | 8778 | SF | 0.62 | 5442.36 | 5442.36
| SUBTOTAL (Mechanical) |  |  |  | 253163.92 | 121511.52 | 131652.4
SUMMARY:
1 | Site |  |  |  | 166706.3 | 166706.3 | 0
2 | Structural |  |  |  | 666742.03 | 666742.03 | 0
3 | Architectural |  |  |  | 234082.36 | 187637.63 | 46444.73
4 | Electrical |  |  |  | 199404.32 | 124347.52 | 75056.8
5 | Mechanical |  |  |  | 253163.92 | 121511.52 | 131652.4
SUBTOTAL (CONSTRUCTION COSTS) |  |  |  |  | 1520098.93 | 1266945 | 253153.93
DESIGN FEES
| Geotechnical Exploration (Estimate) |  |  |  | 4500 | 4500
| Stuctural Engineering |  |  |  | 45552.55 | 45552.55
| Architectural Design |  |  |  | 70828 | 68328 | 2500
| Civil/Survey |  |  |  | 15184 | 15184
| MEP Engineering |  |  |  | 18980 | 18980
| Construction Observation, Administration, As Built Drawings |  |  |  | 11388 | 11388
SUBTOTAL (Design Fees) |  |  |  |  | 166432.55 | 163932.55 | 2500
TOTAL (PROJECT COST)
Project Totals |  |  |  |  | 339050 | 286690 | 57360
| Final Project Cost |  |  |  | 1686531.48
| Total FEMA Elligible Cost |  |  |  | 1430877.55
| Federal Share (75%) |  |  |  | 1073158.1625
| Local Share (25%) |  |  |  | 357719.3875
| Total Non-Elligible FEMA Cost |  |  |  | 255653.93
* Line items and values are examples only

## Tab C2 - Detailed Budget
Detailed Budget Narrative
Request a Budget Summary Spreadsheet template from SEMA to be included as Attachment 7.
Note: A budget narrative supporting the detailed budget and detailed cost estimate is required. The narrative should contain specific information concerning how FEMA eligible vs. non-eligible costs were determined. The budget narrative is identified as a requirement under the Unified HMA Guidance Part IV, Section H.

## Tab D - BCA
Benefit-Cost Analysis
Use the documents on BCA Resource/Tool Kit to prepare the BCA.
Attach an electronic copy of the final BCA to your application email. Attach a paper copy of the final BCA and supporting documentation with your paper application.
Contact the BC Helpdesk or State Mitigation Staff if you need technical assistance.

## Tab E - Safe Room WKST
Instructions: Please complete one Safe Room Application for each Safe Room proposed. Attach additional pages and supporting documentation as necessary.
I. Project Site Owner Information
Owner Name(s):
Owner Mailing Address:
City: | Zip Code:
Phone: | Email:
II. Project Site Information
Building Name:
Street Address:
City: | Zip Code:
Latitude: | Longitude: | (-)
Is the property being purchased, donated by a private owner, or dedicated to Safe Room use by the applicant? | Select One
Purchase of Property
Private donation
Dedication to safe room use by applicant
Will the land value be applied to non-federal match? | Select One
Yes
No
If yes, will the applicant incorporate the appraisal as a pre-award or post-award activity (if the appraisal is a pre-award activity, separate line items MUST be included in the cost estimate for appraisal cost and land value). | Select One
Pre-Award
Post-Award
Not Applicable
Are copies of the tax parcel map and tax record attached, if land is being purchased, donated or dedicated to Safe Room use? | Select One
Yes
No
Is a copy of a city/county map attached? | Select One
Is a copy of a USGS 1:24,000 topographic map attached? | Select One
Is a copy of the FIRM or FHBM attached? | Select One
If access is within the SFHA or 500-year floodplain, describe the alternate means of access to the Safe Room.
Project Area Photographs: | Select One
Attached
Incomplete
Describe the property's current use.
Describe the property's post-mitigation use.
III. Proposed Safe Room Information
Proposed Safe Room Information | Type of Safe Room - Select One
Stand Alone Safe Room (separate building)
Internal Safe Room (within or attached to a building)
New Construction or Retrofit - Select One
New Construction
Retrofit of existing structure
Use - Select One
Single-Use
Multi-Use
If a Retrofit, is the existing facility a critical facility? | Select One
Yes
No
Total Square Footage of entire Proposed Structure:
Total (gross) Square Footage of Proposed Safe Room space:
Usable Square Footage of Proposed Safe Room space:
IV. Mitigation Project Data
Project Useful Life:
Anticipated Safe Room Population During Day:
Anticipated Safe Room Population During Evening:
Anticipated Safe Room Population During Night:
Radius of Community that Will Use the Safe Room (no more than 1/2 mile):
Do window/doors account for less than 7% of building area | Select One
Design/Mapped Wind Speed of 250 MPH (Missouri) Section 3.3 of FEMA 361 | Select One
Required Draft Narrative of Safe Room Operations and Maintenance Plan, including Signage: | Select One
Attached
Incomplete
V. Design and Drawings Information
Required Appendix B.2 Designer Checklist - Completed: |  |  | Select One
Attached
Incomplete
Preliminary or Final Architectural/Engineering Design Plans, including site map showing parking: |  |  | Select One
Attached - Preliminary
Attached - Final
Incomplete
If preliminary design plans, do they include Safe Room dimensions and a site map with parking? (All final design-related documents, QA plan, and Peer Review must be submitted within six months of grant award.) |  |  | Select One
Attached
Incomplete
If retrofit, has the Safe Room to be incorporated been identified on the drawings? |  |  | Select One
Yes
No
Not Applicable
Have the requisite paved handicapped spaces and ADA access into the Safe Room been addressed? |  |  | Select One
Yes
No
Signed & Sealed Peer Review by an Independent Registered Design Professional that the Final Architecture/Engineering Design Plans and Specs Meet FEMA 361 Design Guidelines, including ICC-500 (required when final design plans are submitted for FEMA review): |  |  | Select One
Attached
Incomplete
VI. Required Functional Components
Has Emergency Communications Equipment been included as a component of the Safe Room? |  |  | Select One
Yes
No
Has Emergency Lighting System been included as a component of the Safe Room? (Personal flash lights are permitted where occupancy is less than 50 persons.) |  |  | Select One
Has a source of back-up power generation been included as a component of the Safe Room? |  |  | Select One
Yes
No
Has appropriate Signage been included as a component of the Safe Room? |  |  | Select One
VII. Safe Room Maintenance Cost Information
Annual Projected Maintenance Costs
Base Year of Construction Costs

## Tab F - Generator Worksheet
Instructions: If backup power generation is part of the project, complete one Generator Worksheet for each generator to be purchased and installed. Under the Safe Room Application, FEMA will fund only the capacity required to operate emergency lighting and ventilation when in use as a saferoom. Attach additional pages and supporting documentation as necessary.
I. Project Information
Applicant:
Generator Location:
City: |  | Zip Code:
II. Generator Information
Running Load (KW):
Starting Load (KW):
Is load being stepped in?
Generator Specified (KW):
Generator Voltage:
Generator Phase? |  | Select One
Single Phase
Three Phase
Type of Controls: |  | Select One
Automatic
Manual
Type of Fuel: |  | Select One
Gas
Diesel
Propane
Other
III. Additional Information & Remarks
Information and Remarks:
IV. Certification
I certify that I have conducted an analysis to verify that the calculated loads and generator specifications will meet all requirements of this proposed facility as described in the project application’s Scope of Work to facilitate the mininum ventilation requirements of the safe room at maximum number of occupants based upon an average occupancy time of two hours, as required by FEMA guidelines.
| (Signature) |  | (Date)
| (Printed Name) |  | (Title)
| (Phone Number) |  | (Organization)
Manual
Gas
Diesel
Propane
Other

## Tab G - Local Match Resolution
LOCAL MATCH RESOLUTION #
FOR THE
HAZARD MITIGATION GRANT PROGRAM
WHEREAS, |  |  |  | (hereinafter called "the Subgrantee"), County of
(jurisdiction)
, has made application through the Missouri State Emergency Management Agency
(SEMA) to the Federal Emergency Management Agency (FEMA) for funding from the
Hazard Mitigation Grant Program, in the amount of | [5 empty] | for the total project cost,
and
WHEREAS, the Subgrantee recognizes the fact that this grant is based on a cost share basis with the federal share not exceeding 75% and the non-federal share being a minimum of 25% of the total project cost. The minimum 25% non-federal share can be either cash or in-kind match.
and
THEREFORE, the Subgrantee agrees to provide and make available up to
( |  |  |  |  | dollars) of non-federal funds to be used to meet
the minimum 25% match requirement for this mitigation grant application.
The resolution was passed and approved this |  |  |  |  | day of |  | 20____.
Signatures of Council or Board Members:
Council or Board Member |  |  |  |  | Council or Board Member
Council or Board Member |  |  |  |  | Council or Board Member
Council or Board Member |  |  |  |  | Council or Board Member
Council or Board Member |  |  |  |  | Council or Board Member
Council or Board Member |  |  |  |  | Council or Board Member
I submit this form for inclusion with the HMGP Project Application.
Print Name of Authorized Representative
Authorized Representative's Signature and Date

## Tab H - Authorized Rep
STATE OF MISSOURI
DESIGNATION OF APPLICANT'S AUTHORIZED REPRESENTATIVE
is hereby authorized to execute on behalf of
(Name of Representative)
this mitigation project and to file it with
(Applicant Entity)
Missouri State Emergency Management Agency (SEMA) for the purpose of obtaining financial assistance under the Robert T. Stafford Disaster Relief and Emergency Assistance Act (PL 93-288, as amended).
Signed this |  | Day Of |  | , 20____.
Chief Executive Officer
(Print Name and Title)
(Signature)
Applicant's Authorized Representative
(Print Name and Title)
(Signature)
Attested:
(Print Name and Title)
(Signature)

## Tab I - EHP
Environmental & Historic Preservation Information
The applicant must provide certain environmental and historic preservation information and documentation to the State before the State and FEMA can adequately review any proposed project. Some projects require specific documentation depending upon the project type and its potential effects on the physical, biological and built environment. The following sections will help ensure that you provide the necessary information and documentation for the project you are proposing. Each of the sections below will begin with a specific question, for which you will provide a Yes, No or Unknown response. In each section where you select Yes or Unknown for any answer, please explain your response in the comments section, and provide any further information about this project that could assist the State and FEMA in their reviews.
A. National Historic Preservation Act - Historical Buildings and Structures
Required: A Section 106 Form and process is available at:
https://mostateparks.com/page/84261/section-106-review
Does your project affect, or is it in close proximity to, any buildings or structures 50 years or more in age?
Yes
No
Unknown
If yes, please confirm that you have provided the following:
The property address and original date of construction for each property affected. (This information may be contained in the Property Data Sheet.)
A minimum of four (4) color photos, showing view of proposed location from each point on the compass (Please label the photos accordingly.)
A diagram or USGS 1:24,000 scale quadrangle map, displaying the relationship of each property to the total project area.
To help FEMA evaluate the impact of the project, please indicate any other information you are providing:
Information gathered about potential historic properties in the project area, including any evidence indicating the age of the structure and presence of structures that are listed or eligible for listing on the National Register of Historic Places or within or near a National Register listed or eligible historic district. Sources for this information may include the SHPO, your local planning office, historical societies, or historic preservation organization.
Consideration of how the project design will minimize adverse effects on known or potential historic structures, and any alternatives considered or implemented to avoid or minimize effects on historic structures. Please address and note associated costs in your project budget.
List all supporting documentation pertaining to historic structures attached to this application:
Additional comments regarding historic structures:
B. National Historic Preservation Act - Archeological Resources
Does your project involve disturbance of ground?
If yes, please confirm that you have provided the following:
A description of the ground disturbance by giving the dimensions (area, volume, depth, etc.) and location.
The past use of the area to be disturbed, noting the extent of previously disturbed ground.
Yes
No
Unknown
A diagram or USGS 1:24,000 scale quadrangle map, displaying the relationship of each property to the total project area.
To help FEMA evaluate the impact of the project, please indicate any other information you are providing:
Information gathered about potential historic properties in the project area, including any archeological sites. Include, if possible, a map showing the relation of any identified historic properties to the project area.
List all supporting documentation pertaining to archeological resources attached to this application:
Additional comments regarding archeological resources:
C. Endangered Species Act & Fish and Wildlife Coordination Act
1. Are federally listed threatened or endangered species or their critical habitat present in the area affected by the project?
Yes
No
Unknown
If yes, please confirm that you have provided the following:
Information obtained to identify species in or near the project area. Provide the source and date of the information cited.
To help FEMA evaluate the impact of the project, please indicate any other information you are providing:
Any request for information and associated response from the United States Fish and Wildlife Service (USFWS) or the Missouri Department of Conservation, regarding potential listed species present and potential of the project to impact those species. Required: Link to request and received response from USFWS for the Natural Heritage Review:
https://naturalheritagereview.mdc.mo.gov
List all supporting documentation pertaining to the Endangered Species Act & Fish and Wildlife Coordination Act:
Additional comments regarding the Endangered Species Act & the Fish and Wildlife Coordination Act:
2. Does your project remove or affect vegetation?
Yes
No
Unknown
If yes, please confirm that you have provided the following:
Description of the amount (area) and type of vegetation to be removed or affected.
A site map showing the project area and the extent of vegetation affected.
Photographs or digital images that show both the vegetation affected and the vegetation in context.
To help FEMA evaluate the impact of the project, please indicate any other information you are providing:
List all supporting documentation pertaining to the Endangered Species Act & Fish and Wildlife Coordination Act:
Additional comments regarding vegetation:
3. Is your project in, near (within 200 feet), or likely to affect any type of waterway or body of water?
Yes
No
Unknown
If yes, and the project is not within an existing structure, please confirm that you have provided the following:
A USGS 1:24,000 scale quadrangle map, showing the project activities in relation to all nearby bodies of water (within 200 feet).
Information about the type of water body nearby, including: dimensions, proximity of the project activity to the body of water, and expected and possible changes to the water body, if any. Identify all bodies of water regardless whether you think there may be any effects.
Photographs or digital images that show both the body of water affected and the project area.
To help FEMA evaluate the impact of the project, please indicate any other information you are providing:
Evidence of any discussions with the United States Fish and Wildlife Service (USFWS) or the Missouri Department of Conservation, regarding any potential impacts if there is the potential for the project to affect any body of water.
List all supporting documentation pertaining bodies of water:
Additional comments regarding bodies of water:
D. Clean Water Act, Rivers & Harbors Act and Executive Order 11990 (Protection of Wetlands)
Will the project involve dredging or disposal of dredged material, excavating, adding fill material or result in any modification to bodies of water or wetlands as "waters of the U.S." as identified by the US Army Corps of Engineers or on the National Wetland Inventory?
If yes, please confirm that you have provided the following:
Documentation of the project location on a USGS 1:24,000 scale topographical map or image, and a copy of National Wetlands Inventory map or other available wetlands mapping information.
To help FEMA evaluate the impact of the project, please indicate any other information you are providing:
Request for information and response letter from the US Army Corps of Engineers and/or State resource agencies regarding the potential for wetlands and applicability of permitting requirements.
Evidence of alternatives considered to eliminate or minimize impacts to wetlands.
List all supporting documentation pertaining to bodies of water or wetlands attached to this application:
Additional comments regarding bodies of water or wetlands for your project:
E. Executive Order 11988 (Floodplain Management)
1. Does a Flood Insurance Rate Map (FIRM), Flood Hazard Boundary Map (FHBM), hydrologic study or some other source indicate that the project is located in or will affect a 100-year floodplain, a 500-year floodplain if a critical facility, an identified regulatory floodway, or an area prone to flooding?
If Yes, please indicate in the comments section below any documentation to identify the means or the alternatives considered to eliminate or minimize the impacts to floodplains to help FEMA evaluate the impact of the project. (See the 8 step process found in 44 CFR §9.6.)
Comments regarding E.O. 11988 (Floodplain Management):
2. Does the project alter a watercourse, water flow patterns or a drainage way, regardless of its floodplain designation?
If Yes, please indicate any other information you are providing to help FEMA evaluate the impact of the project:
Hydrologic/hydraulic information from a qualified engineer to demonstrate how drainage and flood flow patterns will be changed and to identify up and down stream effects.
Evidence of consultation with the US Army Corps of Engineers. (May be included under Part D of this section.)
Request for information and response letter from the State waterway resource agency, if applicable, with jurisdiction over modifications of waterways.
List all documentation pertaining to Altering Watercourses, Water Flow Patterns, or Drainage Ways attached to this application:
Additional comments regarding Altering Watercourses, Water Flow Patterns or Drainage Ways:
F. Farmland Protection Policy Act
Will the project convert more than five (5) acres of "prime or unique" farmland outside city limits to non-agricultural use:
List all documentation pertaining the Farmland Protection Policy Act attached to this application:
Additional comments regarding the Farmland Protection Policy Act:
G. RCRA and CERCLA (Hazardous and Toxic Materials)
1. Is there reason to suspect that there are contaminants from a current or past use on the property associated with the proposed project?
If yes, please indicate below any other information you are providing to FEMA to evaluate the impact of the project:
Comments and any relevant documentation.
Results of any consultations with State or local agency to obtain permit with requirements for handling, disposing of or addressing the effects of hazardous or toxic materials related to project implementation.
List all documentation pertaining to Hazardous and Toxic Materials attached to this application:
Additional comments regarding Hazardous and Toxic Materials and your project:
2. Are there any studies, investigations or enforcement actions related to the property associated with the proposed project?
If yes, please indicate below any other information you are providing to FEMA to evaluate the impact of the project:
Comments and any relevant documentation.
Results of any consultations with State or local agency to obtain permit with requirements for handling, disposing of or addressing the effects of hazardous or toxic materials related to project implementation.
List all documentation pertaining to Studies, Investigations or Enforcement Actions attached to this application:
Additional comments regarding Studies, Investigations and Enforcement Actions and your project:
3. Do any project construction or operation activities involve the use of hazardous or toxic materials?
If yes, please indicate below any other information you are providing to FEMA to evaluate the impact of the project:
Comments and any relevant documentation.
Results of any consultations with State or local agency to obtain permit with requirements for handling, disposing of or addressing the effects of hazardous or toxic materials related to project implementation.
List all documentation pertaining to the use of Hazardous and Toxic Materials attached to this application:
Additional comments regarding the use of Hazardous and Toxic Materials and your project:
4. Do you know if any of the current or past land uses of the property affected by the proposed project or of the adjacent properties are associated with Hazardous or Toxic Materials?
If yes, please indicate below any other information you are providing to FEMA to evaluate the impact of the project:
Comments and any relevant documentation.
Results of any consultations with State or local agency to obtain permit with requirements for handling, disposing of or addressing the effects of hazardous or toxic materials related to project implementation.
List all documentation pertaining to the use of Hazardous and Toxic Materials related to Current or Past Land Uses attached to this application:
Additional comments regarding the use of Hazardous and Toxic Materials related to Current or Past Land Uses and your project:
H. Other Environmental / Historic Preservation Laws or Issues
1. Are there other environmental/historic preservation requirements associated with this project that you are aware of?
If yes, please provide a description of the requirements, issues or public involvement effort.
2. Are there controversial issues associated with this project?
If yes, please provide a description of the requirements, issues or public involvement effort.
3. Have you conducted any public meeting or solicited public input or comments on your specific proposed mitigation project?
If yes, please provide a description of the requirements, issues or public involvement effort.
List all documentation pertaining to Other Environmental/Historic Preservation Issues attached to this application:
Additional comments regarding Other Environmental/Historic Preservation Laws:
I. Summary and Cost of Potential Impacts
Having answered the questions in Parts A through H, have you identified any aspects of your proposed project that have the potential to impact environmental resources or historic properties?
Yes
No
Unknown
Yes
No
If yes, please confirm that you have:
Evaluated these potential effects and provided the materials required in Parts A through I that identify the nature and extent of potential impacts to environmental resources and/or historic properties.
Consulted with appropriate parties to identify any measures needed to avoid or minimize these impacts.
Considered alternatives that could minimize both the impacts and the cost of the project.
Made certain that the costs of any measures to treat adverse effects are realistically reflected in the project budget estimate.
Please enter additional comments here:

## Tab J- Supporting Documentation
Safe Room
1 | Table of Contents | Application attachments should be identified within a table of contents.
2 | Safe Room Footprint/Floor plan Drawing | A basic footprint drawing must be submitted showing the safe room envelope, its dimensions, and all interior rooms.
3 | Evacuation/Site Map *Reference FEMA Evacuation/ Site Drill Guidelines & Letter Template | A site map must be attached identifying all the applicable buildings on site and the number of average occupants of each building. The site map should also include the evacuation routes proposed and identification of any potential obstacles to the evacuation routes should any exist (such as railroad tracks, overhead power lines, or major roadways). Safe room parking areas should also be identified on the map.
4 | Half Mile Radius Map | If including the surroudning residences, this map should reflect the half mile radius from the proposed project site that the targeted population must either be located in or reside within. Google Earth can be used to construct this map.
5 | Narrative identifying the target population, methodology of documenting the population numbers, and calculation of the USF/GSF. | Census data is a valuable resource for documenting the number of occupants who reside or are located within a 5 minute walking distance not to exceed a half mile radius of the proposed project site. For fixed populations such as students, faculty, staff, and visitors at a school, documentation of daily attendance, after school activities and attendance, and other records may be provided. Data sources and necessary attachments should be provided in addition to the narrative and calculations describing the square footage derived based on the target population utilizing the safe room. (Population count summary, physical county of residential structures (if applicable), school population letter, census data, safe room area calculation)
6 | SEMA Budget Summary Spreadsheet | See SEMA App Tab C-2 - Detailed Cost Estimate template. Request an electronic copy of this spreadsheet from SEMA
7 | Management Cost For Sub-Recipients Form (SRMC) | Hazard Mitigation Grant Program-Management Cost. Fill out form to verify if or not receiving management cost. (If applicable) (SRMC letter-budget, SRMC Excel spreadsheet)
8 | Letters of support/coordination from the appropriate local emergency response agencies. | Examples of such agencies might include the local EMD, the police department, the fire department and local Red Cross Chapter.
9 | Safe Room Drill Documentation | Any school campus where the target population has to go outside to access the safe room must conduct a drill to ensure that all occupants can travel to the safe room within 5 minutes, as well as being able to access and lock down the safe room within an additional five minutes. Reference the SEMA safe room drill template letter for further guidance.
10 | SHPO Concurrence Letter | If the concurrence letter has not yet been received at the time the app is submitted a copy of the completed Section 106 Form must be attached to the app.
11 | FIRM or FIRMette *Component of SHPO Concurrence Documents | A Flood Insurance Rate Map or section (FIRMette) must be attached to the application. FIRMettes can be created at: www.msc.fema.gov. The proposed safe room location must be marked on the FIRM Map.
12 | Site Photos *Component of SHPO Concurrence Documents | Photos depicting the proposed project site from all four directions must be attached to the application.
13 | Topographical Map *Component of SHPO Concurrence Documents | A TOPO map of the general region including the proposed project site must be attached to the application. The proposed safe room location must be marked on the TOPO Map.
14 | Dept. of Conservation (DOC) Concurrence Letter | The same guidance provided for SHPO concurrence applies to the DOC except that the digital photos are not required.
15 | Operations/Maintenance Plan | A narrative must be attached to the application explaining how an operations and maintenance plan that conforms to FEMA 361, will be developed. The O&M plan narrative should include a statement that the plan will address all elements of Chapter 9, Emergency Management Considerations, of FEMA 361. This narrative is not necessary if a DRAFT O&M plan is available to be submitted in conjunction with the submission of the initial application.
16 | Local Mitigation Plan Resolution of Adoption | Copy of the adoption resolution from the currently approved local hazard mitigation plan. The project Mitigation Action Item is required to be in the local hazard mitigation plan to be eligible, but not required to include in application.
17 | IF APPLICABLE: Assurance of Safe Room being designed and constructed by seismic code per E.O. 12699 and MO Revised Statute 319, Section 319.200 | Any safe room proposed to be constructed in one of the 47 counties identified as being at high risk from earthquakes must submit a signed and dated assurance letter on the sub-applicant's official letterhead confirming that the safe room will be constructed in compliance with the most current seismic construction standards.
18 | Additional Supporting Documentation | FEMA requires that any significant application element be verified by attaching adequate supporting documentation. (latitidue/Longitude map, detailed cost estimate narrative, detailed cost estimate, storm data)
19 | BCA | Benefit Cost Analysis https://www.fema.gov/grants/tools/benefit-cost-analysis
20 | SRDA | Safe Room Design Assurance Letter

## SEMA Budget Sheet
*Remember to submit a detailed Cost Estimate along with the Budget Information form*
**A "print area" has been set for this document. Simply print as you normally would and the document should fit on a single page.**
= Formula Cells (Do not change these cells)
= Editable Cells (Input your information here)
SEMA Budget Information - Construction Projects
Project: |  | Grant: |  |  | Preparer: |  |  |  | Date:
Cost Classification |  | a. Total Cost |  |  | b. FEMA Eligible Cost |  |  | c. FEMA Ineligible Cost
1. Preliminary Expense (if applicable)
|  | $ |  |  | $ |  |  | $ | 0
2. Project Management Expense
|  | $ |  |  | $ |  |  | $ | 0
(not to exceed 5% of total project costs; includes line a. below, if applicable)
a. Operations & Maintenance Plan
$
(optional; not to exceed 5% of non-construction costs)
3. Architectural Engineering Basic Fees
|  | $ |  |  | $ |  |  | $ | 0
Total Non-Construction Costs - (Sub-grant Phase 1)
|  | $ | 0 |  | $ | 0 |  | $ | 0
4. Project Inspection Fees
|  | $ |  |  | $ |  |  | $ | 0
5. Land (Site) Development
|  | $ |  |  | $ |  |  | $ | 0
6. Equipment (Generator, transfer switch, installation costs only)
|  | $ |  |  | $ |  |  | $ | 0
7. Construction and Project Improvement
a. General Construction Expenses
|  | $ |  |  | $ |  |  | $ | 0
b. Plumbing
|  | $ |  |  | $ |  |  | $ | 0
c. Electrical
|  | $ |  |  | $ |  |  | $ | 0
d. HVAC (Ventilation costs are the only FEMA Eligible costs)
|  | $ |  |  | $ |  |  | $ | 0
Total Project Costs
|  | $ | 0 |  | $ | 0 |  | $ | 0
FEDERAL FUNDING
Enter as a % (i.e. ##%) or decimal (.##)
Federal assistance requested, calculate as follows: |  | $ | 0 |  | Multiply by: |  | 75% | $ | 0
(Consult Federal agency for percentage share.) |  | Total Eligible Project Costs |  |  |  |  | Federal % Share | Total Federal Project Share
NON-FEDERAL FUNDING
Enter as a % (i.e. ##%) or decimal (.##)
Non-Federal share, calculate as follows: |  | $ | 0 |  | Multiply by: |  | 25% | $ | 0
(Consult Federal agency for percentage share.) |  | Total Eligible Project Costs |  |  |  |  | Non-FED % Share | Total Non-FED Project Share